## Sheet1
Risk ID | Risk Description | Risk Category | Likelihood | Impact | Severity | Mitigation Strategy | Contingency Plan
R1 | System downtime during implementation | Technical | High | High | High | Use cloud infrastructure, backup systems, phased deployment | Activate backup servers and rollback to previous stable version. Notify stakeholders immediately and switch to manual scheduling temporarily until system is restored.
R2 | Data breach or security vulnerability | Technical | Medium | High | High | Implement encryption, access control, regular audits | Isolate affected systems, initiate incident response protocol, notify regulatory authorities, reset credentials, and restore data from secure backups.
R3 | Staff resistance to new system | Operational | High | Medium | High | Conduct training sessions, change management programs | Deploy additional on-site support team, provide immediate hands-on assistance, temporarily allow hybrid (manual + system) usage until adoption improves.
R4 | Inaccurate or incomplete data migration | Technical | Medium | High | High | Data validation, testing, backup before migration | Roll back to backup dataset, pause system usage, re-run migration after validation, and manually verify critical records before go-live.
R5 | Workflow disruption during transition | Operational | High | Medium | High | Pilot testing, phased rollout | Revert to legacy workflows temporarily, implement phased rollout, assign supervisors to monitor operations and resolve issues in real-time.
R6 | Poor user adoption (patients/staff) | Stakeholder | Medium | High | High | User-friendly UI, awareness campaigns | Launch emergency awareness campaigns, provide quick training sessions, introduce helpdesk support, and simplify system interfaces if required.
R7 | Misalignment between stakeholders | Stakeholder | Medium | Medium | Medium | Regular meetings, stakeholder engagement plan
R8 | Resource shortages during peak time | Operational | High | Medium | High | Real-time resource tracking system | Reallocate resources dynamically, prioritize critical patients, temporarily extend working hours or redistribute workload across departments.
R9 | Integration failure between systems | Technical | Medium | High | High | API testing, modular integration approach | Disable faulty integration module, operate systems independently, use manual data transfer temporarily, and fix integration through patches.
R10 | Budget overruns | Operational | Medium | Medium | Medium | Budget monitoring, phased implementation
R11 | Regulatory non-compliance | Technical | Low | High | Medium | Ensure compliance audits (HIPAA-like standards)
R12 | Delays in project timeline | Operational | Medium | Medium | Medium | Proper project planning and tracking
| Impact: Low | Impact: Medium | Impact: High
Likelihood: High | Medium | High | High
Likelihood: Medium | Low | Medium | High
Likelihood: Low | Low | Low | Medium