## Sheet1
WBS ID | Task Name | Task Description | Owner | Milestone/Deliverable | Estimated Duration
1 | Project Initiation | Define project scope and objectives | Project Manager | Project Kick-off | 2 days
1.1 | Requirements Gathering | Collect and document business requirements | Business Analyst | Requirements Document (BRD) | 1 week
1.1.1 | Stakeholder Interviews | Gather stakeholder feedback | Business Analyst | Stakeholder Feedback Report | 2 days
1.1.2 | Data Analysis | Analyze appointment, resource, and feedback datasets | Data Analyst | Data Insights Report | 3 days
1.2 | Requirement Validation | Validate requirements with stakeholders | Business Analyst | Approved Requirements | 2 days
1.3 | RTM & Stakeholder Plan | Create RTM and stakeholder engagement plan | Business Analyst | RTM & Stakeholder Matrix | 2 days
2 | System Design | Design system architecture and workflows | IT Team | System Design Document | 1 week
2.1 | Scheduling System Design | Design automated scheduling module | IT Team | Scheduling System Design | 3 days
2.2 | Resource Management Design | Design resource tracking system | IT Team | Resource Module Design | 3 days
2.3 | Communication System Design | Design notification system | IT Team | Notification Design | 2 days
3 | Development Phase | Develop system modules | IT Team | Functional System Prototype | 2 weeks
3.1 | Appointment System Development | Build scheduling system | IT Team | Scheduling Module | 5 days
3.2 | EHR System Development | Develop centralized records system | IT Team | EHR Module | 5 days
3.3 | Dashboard Development | Build analytics dashboards | Data Analyst | Dashboard Prototype | 4 days
3.4 | Notification System Development | Implement SMS/email alerts | IT Team | Notification System | 3 days
4 | Testing Phase | Test system functionality and performance | QA Team | Test Report | 1 week
4.1 | Functional Testing | Validate system features | QA Team | Functional Test Results | 3 days
4.2 | Performance Testing | Check system speed and reliability | QA Team | Performance Report | 2 days
4.3 | User Acceptance Testing | Validate system with stakeholders | Stakeholders | UAT Approval | 2 days
5 | Deployment | Deploy system in hospital environment | IT Team | System Deployment | 3 days
5.1 | Training | Train staff on new system | Business Analyst / IT | Training Completion | 2 days
5.2 | Go-Live Support | Monitor system post-launch | IT Team | System Stabilization | 3 days
6 | Project Closure | Final documentation and reporting | Project Manager | Project Closure Report | 2 days